## Summary
Daily Incident Report — June 17, 2026
Period: June 17, 2026 · 18:00 IST
Status | Count | % of Total
Open | 8 | 16.3%
In Progress | 20 | 40.8%
On Hold | 10 | 20.4%
Awaiting Resolution Confirmation | 11 | 22.4%
Total | 49 | 100%

## All Tickets
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Reason | Last Updated | Created
#217606 | Otsuka | Gold | Login Issue with CoreStack Tool | P3 | Open | 13d | 8-14d | L1 |  | Rajkumar U |  | 17 Jun 2026 | Jun 04
#219258 | CoreStack SRE | Bronze | Firing: [High Priority] MSProd App Server Memory Utilisation above 90% | P3 | Open | 9d | 8-14d | L1 |  | SRE Monitor |  | 08 Jun 2026 | Jun 08
#219898 | Cloud Kinetics | Silver | Deployment Status Confirmation Required | P3 | Open | 7d | 0-7d | L1 |  | Cloud Kinetics SA |  | 17 Jun 2026 | Jun 10
#220999 | Core42 | Bronze | Request for Investigation – OCI Cost Processing and Cost Optimizer Issues | P3 | Open | 5d | 0-7d | L1 |  | Muthu D |  | 17 Jun 2026 | Jun 12
#222219 | Otsuka | Gold | Request for Azure DevOps Cost Details at Resource Level | P3 | Open | 2d | 0-7d | L1 |  | Rajkumar U |  | 16 Jun 2026 | Jun 15
#222287 | Otsuka | Gold | Confirmation Request – AI (LLM) Cost Details | P3 | Open | 2d | 0-7d | L1 |  | Rajkumar U |  | 16 Jun 2026 | Jun 15
#223020 | CoreStack SRE | Bronze | Firing: [Critical] MSProd-graphdb-01 server load average above 2 | P3 | Open | 0d | 0-7d | L1 |  | SRE Monitor |  | 17 Jun 2026 | Jun 17
#223026 | CoreStack SRE | Bronze | Resolved: [Critical] MSProd-graphdb-01 server load average above 2 | P3 | Open | 0d | 0-7d | L1 |  | SRE Monitor |  | 17 Jun 2026 | Jun 17
#222922 | GE Vernova | Bronze | Memory Spike in GEV Dedicated Prod Environment | P3 | In Progress | 0d | 0-7d | L1 |  | Vijaykumar P |  | 17 Jun 2026 | Jun 17
#222173 | Exide | Bronze | PoV Exide: Unable to execute CIS compliance standard | P3 | In Progress | 2d | 0-7d | L1 |  | Nagalakshmi N |  | 17 Jun 2026 | Jun 15
#222571 | Sonata Software | Bronze | Re: CoreStack - FinOps. Call | P2 | In Progress | 1d | 0-7d | L1 |  | Deovrat S |  | 17 Jun 2026 | Jun 16
#222547 | Otsuka | Gold | Request for Review of Optimization Recommendations (SKU Marked as NA) | P3 | In Progress | 1d | 0-7d | L1 |  | Rajkumar U |  | 16 Jun 2026 | Jun 16
#222218 | Aliando | Bronze | Enable FinOps Governance Summary Report ¦ QapiPlus | P3 | In Progress | 2d | 0-7d | L1 |  | Ajit T |  | 16 Jun 2026 | Jun 15
#222619 | CoreStack | Bronze | FinOps Governance Summary Report ¦ Month field not able to select | P3 | In Progress | 1d | 0-7d | L1 |  | Jayven C |  | 16 Jun 2026 | Jun 16
#219593 | Microland | Bronze | Issue with Budget Report Month Selection and Financial Year Setup | P3 | In Progress | 8d | 8-14d | L1 |  | Senapathi R |  | 16 Jun 2026 | Jun 09
#222463 | Sonata Software | Bronze | Mismatch in Cost Figures Between Azure Cost Management and CoreStack FinOps | P3 | In Progress | 1d | 0-7d | L1 |  | Thadi S |  | 16 Jun 2026 | Jun 16
#222461 | Kyndryl | Gold | Kyndryl SaaS Okta SSO Configuration | P3 | In Progress | 1d | 0-7d | L1 |  | Nagalakshmi N |  | 16 Jun 2026 | Jun 16
#222257 | Sonata Software | Bronze | Arcera - Replace PAYG to CSP Onboarding | P3 | In Progress | 2d | 0-7d | L1 |  | Krishnakumar VJ |  | 15 Jun 2026 | Jun 15
#222040 | LTTS | Bronze | Billing Amount Difference between GCP and CoreStack | P3 | In Progress | 2d | 0-7d | L1 |  | Kaustubh M |  | 15 Jun 2026 | Jun 15
#222003 | SHI Locuz | Bronze | SHI Locuz - Need Assistance in Compliance Execution & Scheduling | P3 | In Progress | 2d | 0-7d | L1 |  | Nagalakshmi N |  | 15 Jun 2026 | Jun 15
#220546 | Blackstone | Bronze | ODP/Blackstone - Bus Patrol | P3 | In Progress | 6d | 0-7d | L1 |  | Jayven C |  | 11 Jun 2026 | Jun 11
#220105 | CoreStack | Bronze | Merged cells in cost recommendation Report | P3 | In Progress | 7d | 0-7d | L1 |  | Nagalakshmi N |  | 10 Jun 2026 | Jun 10
#219541 | Sonata Software | Bronze | Trustech - FinOps not triggered | P2 | In Progress | 8d | 8-14d | L1 |  | Krishnakumar VJ |  | 09 Jun 2026 | Jun 09
#216750 | Tata Communications | Gold | FW: Production Environment ¦ IFoundry5X | P3 | In Progress | 15d | 15-30d | L1 |  | Sunilkumar S |  | 09 Jun 2026 | Jun 02
#216808 | Kyndryl | Gold | Difference Between CoreStack Recommendation and Azure Calculator Pricing | P3 | In Progress | 15d | 15-30d | L1 |  | Randhir K |  | 04 Jun 2026 | Jun 02
#217515 | Kyndryl | Gold | FW: Cost Mismatch in recommendation (Kyndryl) | P3 | In Progress | 13d | 8-14d | L1 |  | Nagalakshmi N |  | 04 Jun 2026 | Jun 04
#211192 | Tata Communications | Gold | FinOps Email Notification Issue (Clone) | P3 | In Progress | 29d | 15-30d | L1 |  | Sunilkumar S |  | 19 May 2026 | May 19
#206833 | Synoptek | Gold | Mar26 usage for Mitsui Chemicals | P3 | In Progress | 41d | 30d+ | L1 |  | S Zborowski |  | 07 May 2026 | May 07
#211893 | Neurealm | Platinum | Re: Core stock FinOps Dashboard cost differ | P2 | On Hold | 27d | 15-30d | L1 |  | Parthasarathy K |  | 15 Jun 2026 | May 21
#211895 | Neurealm | Platinum | Re: Core stock FinOps Dashboard cost differ for GCP | P3 | On Hold | 27d | 15-30d | L1 |  | Parthasarathy K |  | 15 Jun 2026 | May 21
#220491 | LifeLabs | Bronze | FW: Resources Cost - Beside Tagged and untagged - LifeLabs | P3 | On Hold | 6d | 0-7d | L1 |  | Nagalakshmi N |  | 15 Jun 2026 | Jun 11
#219147 | Sonata Software | Bronze | RE: CUR Backfill | P3 | On Hold | 9d | 8-14d | L1 |  | Raghavan P |  | 13 Jun 2026 | Jun 08
#217990 | CoreStack | Bronze | cloud.corestack.io is slow across all pages | P3 | On Hold | 12d | 8-14d | L1 |  | Satya C |  | 12 Jun 2026 | Jun 05
#205888 | Logicalis | Gold | Need assistance to update creds for EA account for Trinity College | P2 | On Hold | 43d | 30d+ | L1 |  | Kamran W |  | 12 Jun 2026 | May 05
#217785 | Cloud Kinetics | Silver | RDS Snapshot Not Created on May 31 | P3 | On Hold | 12d | 8-14d | L1 |  | Cloud Kinetics SA |  | 11 Jun 2026 | Jun 05
#217961 | Sonata Software | Bronze | Sonata - CSP accounts not showing up | P3 | On Hold | 12d | 8-14d | L1 |  | Deovrat S |  | 09 Jun 2026 | Jun 05
#219360 | CoreStack | Bronze | cloud.corestack.io | P3 | On Hold | 9d | 8-14d | L1 |  | Satya C |  | 08 Jun 2026 | Jun 08
#211954 | Otsuka | Gold | AWS Accounts transfer from INH to ISO Tenant | P3 | On Hold | 27d | 15-30d | L1 |  | Rajkumar U |  | 22 May 2026 | May 21
#222615 | Logicalis | Gold | Unable to login in Logicalis Cloud Management Portal (CMP) | P3 | Awaiting Resolution Confirmation | 1d | 0-7d | L1 |  | Julio A |  | 17 Jun 2026 | Jun 16
#222631 | CoreStack | Bronze | Taylor Farms - Graphion SBOM workflow - Infra scans getting skipped | P3 | Awaiting Resolution Confirmation | 1d | 0-7d | L1 |  | A Bagchi |  | 16 Jun 2026 | Jun 16
#220875 | Synopsys | Gold | Dashboard slowness | P2 | Awaiting Resolution Confirmation | 5d | 0-7d | L1 |  | Ranjitha T |  | 15 Jun 2026 | Jun 12
#221054 | Kyndryl | Gold | US SaaS - Kyndryl - Default dashboards not visible for tenant/finops_admin | P3 | Awaiting Resolution Confirmation | 5d | 0-7d | L1 |  | Nagalakshmi N |  | 12 Jun 2026 | Jun 12
#220416 | Sonata Software | Bronze | Sonata - Tata Tele CSP processing issue | P2 | Awaiting Resolution Confirmation | 6d | 0-7d | L1 |  | Deovrat S |  | 12 Jun 2026 | Jun 11
#220165 | Sonata Software | Bronze | Trustedtech - HMH - cost for April | P3 | Awaiting Resolution Confirmation | 7d | 0-7d | L1 |  | Krishnakumar VJ |  | 10 Jun 2026 | Jun 10
#219989 | Sonata Software | Bronze | Re: Corestack | P3 | Awaiting Resolution Confirmation | 7d | 0-7d | L1 |  | Deovrat S |  | 10 Jun 2026 | Jun 10
#219658 | CoreStack | Bronze | US Prod - Dashboard Not Loading | P3 | Awaiting Resolution Confirmation | 8d | 8-14d | L1 |  | Ashokkumar E |  | 09 Jun 2026 | Jun 09
#219377 | Blackstone | Bronze | ODP Corporation MCA Billing Account cost processing errors | P3 | Awaiting Resolution Confirmation | 9d | 8-14d | L1 |  | Jayven C |  | 08 Jun 2026 | Jun 08
#219361 | Getronics | Silver | Filtrona ¦ FinOps Dashboard ¦ Unallocated Resource Groups | P3 | Awaiting Resolution Confirmation | 9d | 8-14d | L1 |  | Shashank N |  | 08 Jun 2026 | Jun 08
#216586 | CoreStack | Bronze | Unable to onboard Snowflake in CS4CS | P3 | Awaiting Resolution Confirmation | 16d | 15-30d | L1 |  | A Bagchi |  | 05 Jun 2026 | Jun 01

## Platinum Gold Silver
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Reason | Last Updated | Created
#217606 | Otsuka | Gold | Login Issue with CoreStack Tool | P3 | Open | 13d | 8-14d | L1 |  | Rajkumar U |  | 17 Jun 2026 | Jun 04
#219898 | Cloud Kinetics | Silver | Deployment Status Confirmation Required | P3 | Open | 7d | 0-7d | L1 |  | Cloud Kinetics SA |  | 17 Jun 2026 | Jun 10
#222219 | Otsuka | Gold | Request for Azure DevOps Cost Details at Resource Level | P3 | Open | 2d | 0-7d | L1 |  | Rajkumar U |  | 16 Jun 2026 | Jun 15
#222287 | Otsuka | Gold | Confirmation Request – AI (LLM) Cost Details | P3 | Open | 2d | 0-7d | L1 |  | Rajkumar U |  | 16 Jun 2026 | Jun 15
#222547 | Otsuka | Gold | Request for Review of Optimization Recommendations (SKU Marked as NA) | P3 | In Progress | 1d | 0-7d | L1 |  | Rajkumar U |  | 16 Jun 2026 | Jun 16
#222461 | Kyndryl | Gold | Kyndryl SaaS Okta SSO Configuration | P3 | In Progress | 1d | 0-7d | L1 |  | Nagalakshmi N |  | 16 Jun 2026 | Jun 16
#216750 | Tata Communications | Gold | FW: Production Environment ¦ IFoundry5X | P3 | In Progress | 15d | 15-30d | L1 |  | Sunilkumar S |  | 09 Jun 2026 | Jun 02
#216808 | Kyndryl | Gold | Difference Between CoreStack Recommendation and Azure Calculator Pricing | P3 | In Progress | 15d | 15-30d | L1 |  | Randhir K |  | 04 Jun 2026 | Jun 02
#217515 | Kyndryl | Gold | FW: Cost Mismatch in recommendation (Kyndryl) | P3 | In Progress | 13d | 8-14d | L1 |  | Nagalakshmi N |  | 04 Jun 2026 | Jun 04
#211192 | Tata Communications | Gold | FinOps Email Notification Issue (Clone) | P3 | In Progress | 29d | 15-30d | L1 |  | Sunilkumar S |  | 19 May 2026 | May 19
#206833 | Synoptek | Gold | Mar26 usage for Mitsui Chemicals | P3 | In Progress | 41d | 30d+ | L1 |  | S Zborowski |  | 07 May 2026 | May 07
#211893 | Neurealm | Platinum | Re: Core stock FinOps Dashboard cost differ | P2 | On Hold | 27d | 15-30d | L1 |  | Parthasarathy K |  | 15 Jun 2026 | May 21
#211895 | Neurealm | Platinum | Re: Core stock FinOps Dashboard cost differ for GCP | P3 | On Hold | 27d | 15-30d | L1 |  | Parthasarathy K |  | 15 Jun 2026 | May 21
#205888 | Logicalis | Gold | Need assistance to update creds for EA account for Trinity College | P2 | On Hold | 43d | 30d+ | L1 |  | Kamran W |  | 12 Jun 2026 | May 05
#217785 | Cloud Kinetics | Silver | RDS Snapshot Not Created on May 31 | P3 | On Hold | 12d | 8-14d | L1 |  | Cloud Kinetics SA |  | 11 Jun 2026 | Jun 05
#211954 | Otsuka | Gold | AWS Accounts transfer from INH to ISO Tenant | P3 | On Hold | 27d | 15-30d | L1 |  | Rajkumar U |  | 22 May 2026 | May 21
#222615 | Logicalis | Gold | Unable to login in Logicalis Cloud Management Portal (CMP) | P3 | Awaiting Resolution Confirmation | 1d | 0-7d | L1 |  | Julio A |  | 17 Jun 2026 | Jun 16
#220875 | Synopsys | Gold | Dashboard slowness | P2 | Awaiting Resolution Confirmation | 5d | 0-7d | L1 |  | Ranjitha T |  | 15 Jun 2026 | Jun 12
#221054 | Kyndryl | Gold | US SaaS - Kyndryl - Default dashboards not visible for tenant/finops_admin | P3 | Awaiting Resolution Confirmation | 5d | 0-7d | L1 |  | Nagalakshmi N |  | 12 Jun 2026 | Jun 12
#219361 | Getronics | Silver | Filtrona ¦ FinOps Dashboard ¦ Unallocated Resource Groups | P3 | Awaiting Resolution Confirmation | 9d | 8-14d | L1 |  | Shashank N |  | 08 Jun 2026 | Jun 08

## New
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Last Updated | Created
#217606 | Otsuka | Gold | Login Issue with CoreStack Tool | P3 | Open | 13d | 8-14d | L1 |  | Rajkumar U | 17 Jun 2026 | Jun 04
#219258 | CoreStack SRE | Bronze | Firing: [High Priority] MSProd App Server Memory Utilisation above 90% | P3 | Open | 9d | 8-14d | L1 |  | SRE Monitor | 08 Jun 2026 | Jun 08
#219898 | Cloud Kinetics | Silver | Deployment Status Confirmation Required | P3 | Open | 7d | 0-7d | L1 |  | Cloud Kinetics SA | 17 Jun 2026 | Jun 10
#220999 | Core42 | Bronze | Request for Investigation – OCI Cost Processing and Cost Optimizer Issues | P3 | Open | 5d | 0-7d | L1 |  | Muthu D | 17 Jun 2026 | Jun 12
#222219 | Otsuka | Gold | Request for Azure DevOps Cost Details at Resource Level | P3 | Open | 2d | 0-7d | L1 |  | Rajkumar U | 16 Jun 2026 | Jun 15
#222287 | Otsuka | Gold | Confirmation Request – AI (LLM) Cost Details | P3 | Open | 2d | 0-7d | L1 |  | Rajkumar U | 16 Jun 2026 | Jun 15
#223020 | CoreStack SRE | Bronze | Firing: [Critical] MSProd-graphdb-01 server load average above 2 | P3 | Open | 0d | 0-7d | L1 |  | SRE Monitor | 17 Jun 2026 | Jun 17
#223026 | CoreStack SRE | Bronze | Resolved: [Critical] MSProd-graphdb-01 server load average above 2 | P3 | Open | 0d | 0-7d | L1 |  | SRE Monitor | 17 Jun 2026 | Jun 17

## In Progress
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Last Updated | Created
#222922 | GE Vernova | Bronze | Memory Spike in GEV Dedicated Prod Environment | P3 | In Progress | 0d | 0-7d | L1 |  | Vijaykumar P | 17 Jun 2026 | Jun 17
#222173 | Exide | Bronze | PoV Exide: Unable to execute CIS compliance standard | P3 | In Progress | 2d | 0-7d | L1 |  | Nagalakshmi N | 17 Jun 2026 | Jun 15
#222571 | Sonata Software | Bronze | Re: CoreStack - FinOps. Call | P2 | In Progress | 1d | 0-7d | L1 |  | Deovrat S | 17 Jun 2026 | Jun 16
#222547 | Otsuka | Gold | Request for Review of Optimization Recommendations (SKU Marked as NA) | P3 | In Progress | 1d | 0-7d | L1 |  | Rajkumar U | 16 Jun 2026 | Jun 16
#222218 | Aliando | Bronze | Enable FinOps Governance Summary Report ¦ QapiPlus | P3 | In Progress | 2d | 0-7d | L1 |  | Ajit T | 16 Jun 2026 | Jun 15
#222619 | CoreStack | Bronze | FinOps Governance Summary Report ¦ Month field not able to select | P3 | In Progress | 1d | 0-7d | L1 |  | Jayven C | 16 Jun 2026 | Jun 16
#219593 | Microland | Bronze | Issue with Budget Report Month Selection and Financial Year Setup | P3 | In Progress | 8d | 8-14d | L1 |  | Senapathi R | 16 Jun 2026 | Jun 09
#222463 | Sonata Software | Bronze | Mismatch in Cost Figures Between Azure Cost Management and CoreStack FinOps | P3 | In Progress | 1d | 0-7d | L1 |  | Thadi S | 16 Jun 2026 | Jun 16
#222461 | Kyndryl | Gold | Kyndryl SaaS Okta SSO Configuration | P3 | In Progress | 1d | 0-7d | L1 |  | Nagalakshmi N | 16 Jun 2026 | Jun 16
#222257 | Sonata Software | Bronze | Arcera - Replace PAYG to CSP Onboarding | P3 | In Progress | 2d | 0-7d | L1 |  | Krishnakumar VJ | 15 Jun 2026 | Jun 15
#222040 | LTTS | Bronze | Billing Amount Difference between GCP and CoreStack | P3 | In Progress | 2d | 0-7d | L1 |  | Kaustubh M | 15 Jun 2026 | Jun 15
#222003 | SHI Locuz | Bronze | SHI Locuz - Need Assistance in Compliance Execution & Scheduling | P3 | In Progress | 2d | 0-7d | L1 |  | Nagalakshmi N | 15 Jun 2026 | Jun 15
#220546 | Blackstone | Bronze | ODP/Blackstone - Bus Patrol | P3 | In Progress | 6d | 0-7d | L1 |  | Jayven C | 11 Jun 2026 | Jun 11
#220105 | CoreStack | Bronze | Merged cells in cost recommendation Report | P3 | In Progress | 7d | 0-7d | L1 |  | Nagalakshmi N | 10 Jun 2026 | Jun 10
#219541 | Sonata Software | Bronze | Trustech - FinOps not triggered | P2 | In Progress | 8d | 8-14d | L1 |  | Krishnakumar VJ | 09 Jun 2026 | Jun 09
#216750 | Tata Communications | Gold | FW: Production Environment ¦ IFoundry5X | P3 | In Progress | 15d | 15-30d | L1 |  | Sunilkumar S | 09 Jun 2026 | Jun 02
#216808 | Kyndryl | Gold | Difference Between CoreStack Recommendation and Azure Calculator Pricing | P3 | In Progress | 15d | 15-30d | L1 |  | Randhir K | 04 Jun 2026 | Jun 02
#217515 | Kyndryl | Gold | FW: Cost Mismatch in recommendation (Kyndryl) | P3 | In Progress | 13d | 8-14d | L1 |  | Nagalakshmi N | 04 Jun 2026 | Jun 04
#211192 | Tata Communications | Gold | FinOps Email Notification Issue (Clone) | P3 | In Progress | 29d | 15-30d | L1 |  | Sunilkumar S | 19 May 2026 | May 19
#206833 | Synoptek | Gold | Mar26 usage for Mitsui Chemicals | P3 | In Progress | 41d | 30d+ | L1 |  | S Zborowski | 07 May 2026 | May 07

## On Hold
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Reason | Last Updated | Created
#211893 | Neurealm | Platinum | Re: Core stock FinOps Dashboard cost differ | P2 | On Hold | 27d | 15-30d | L1 |  | Parthasarathy K |  | 15 Jun 2026 | May 21
#211895 | Neurealm | Platinum | Re: Core stock FinOps Dashboard cost differ for GCP | P3 | On Hold | 27d | 15-30d | L1 |  | Parthasarathy K |  | 15 Jun 2026 | May 21
#220491 | LifeLabs | Bronze | FW: Resources Cost - Beside Tagged and untagged - LifeLabs | P3 | On Hold | 6d | 0-7d | L1 |  | Nagalakshmi N |  | 15 Jun 2026 | Jun 11
#219147 | Sonata Software | Bronze | RE: CUR Backfill | P3 | On Hold | 9d | 8-14d | L1 |  | Raghavan P |  | 13 Jun 2026 | Jun 08
#217990 | CoreStack | Bronze | cloud.corestack.io is slow across all pages | P3 | On Hold | 12d | 8-14d | L1 |  | Satya C |  | 12 Jun 2026 | Jun 05
#205888 | Logicalis | Gold | Need assistance to update creds for EA account for Trinity College | P2 | On Hold | 43d | 30d+ | L1 |  | Kamran W |  | 12 Jun 2026 | May 05
#217785 | Cloud Kinetics | Silver | RDS Snapshot Not Created on May 31 | P3 | On Hold | 12d | 8-14d | L1 |  | Cloud Kinetics SA |  | 11 Jun 2026 | Jun 05
#217961 | Sonata Software | Bronze | Sonata - CSP accounts not showing up | P3 | On Hold | 12d | 8-14d | L1 |  | Deovrat S |  | 09 Jun 2026 | Jun 05
#219360 | CoreStack | Bronze | cloud.corestack.io | P3 | On Hold | 9d | 8-14d | L1 |  | Satya C |  | 08 Jun 2026 | Jun 08
#211954 | Otsuka | Gold | AWS Accounts transfer from INH to ISO Tenant | P3 | On Hold | 27d | 15-30d | L1 |  | Rajkumar U |  | 22 May 2026 | May 21

## Awaiting Resolution
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Reason | Last Updated | Created
#222615 | Logicalis | Gold | Unable to login in Logicalis Cloud Management Portal (CMP) | P3 | Awaiting Resolution Confirmation | 1d | 0-7d | L1 |  | Julio A |  | 17 Jun 2026 | Jun 16
#222631 | CoreStack | Bronze | Taylor Farms - Graphion SBOM workflow - Infra scans getting skipped | P3 | Awaiting Resolution Confirmation | 1d | 0-7d | L1 |  | A Bagchi |  | 16 Jun 2026 | Jun 16
#220875 | Synopsys | Gold | Dashboard slowness | P2 | Awaiting Resolution Confirmation | 5d | 0-7d | L1 |  | Ranjitha T |  | 15 Jun 2026 | Jun 12
#221054 | Kyndryl | Gold | US SaaS - Kyndryl - Default dashboards not visible for tenant/finops_admin | P3 | Awaiting Resolution Confirmation | 5d | 0-7d | L1 |  | Nagalakshmi N |  | 12 Jun 2026 | Jun 12
#220416 | Sonata Software | Bronze | Sonata - Tata Tele CSP processing issue | P2 | Awaiting Resolution Confirmation | 6d | 0-7d | L1 |  | Deovrat S |  | 12 Jun 2026 | Jun 11
#220165 | Sonata Software | Bronze | Trustedtech - HMH - cost for April | P3 | Awaiting Resolution Confirmation | 7d | 0-7d | L1 |  | Krishnakumar VJ |  | 10 Jun 2026 | Jun 10
#219989 | Sonata Software | Bronze | Re: Corestack | P3 | Awaiting Resolution Confirmation | 7d | 0-7d | L1 |  | Deovrat S |  | 10 Jun 2026 | Jun 10
#219658 | CoreStack | Bronze | US Prod - Dashboard Not Loading | P3 | Awaiting Resolution Confirmation | 8d | 8-14d | L1 |  | Ashokkumar E |  | 09 Jun 2026 | Jun 09
#219377 | Blackstone | Bronze | ODP Corporation MCA Billing Account cost processing errors | P3 | Awaiting Resolution Confirmation | 9d | 8-14d | L1 |  | Jayven C |  | 08 Jun 2026 | Jun 08
#219361 | Getronics | Silver | Filtrona ¦ FinOps Dashboard ¦ Unallocated Resource Groups | P3 | Awaiting Resolution Confirmation | 9d | 8-14d | L1 |  | Shashank N |  | 08 Jun 2026 | Jun 08
#216586 | CoreStack | Bronze | Unable to onboard Snowflake in CS4CS | P3 | Awaiting Resolution Confirmation | 16d | 15-30d | L1 |  | A Bagchi |  | 05 Jun 2026 | Jun 01

## L2 Tickets
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Last Updated | Created

## Aging View
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Reason | Last Updated | Created
#206833 | Synoptek | Gold | Mar26 usage for Mitsui Chemicals | P3 | In Progress | 41d | 30d+ | L1 |  | S Zborowski |  | 07 May 2026 | May 07
#205888 | Logicalis | Gold | Need assistance to update creds for EA account for Trinity College | P2 | On Hold | 43d | 30d+ | L1 |  | Kamran W |  | 12 Jun 2026 | May 05
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Reason | Last Updated | Created
#216750 | Tata Communications | Gold | FW: Production Environment ¦ IFoundry5X | P3 | In Progress | 15d | 15-30d | L1 |  | Sunilkumar S |  | 09 Jun 2026 | Jun 02
#216808 | Kyndryl | Gold | Difference Between CoreStack Recommendation and Azure Calculator Pricing | P3 | In Progress | 15d | 15-30d | L1 |  | Randhir K |  | 04 Jun 2026 | Jun 02
#211192 | Tata Communications | Gold | FinOps Email Notification Issue (Clone) | P3 | In Progress | 29d | 15-30d | L1 |  | Sunilkumar S |  | 19 May 2026 | May 19
#211893 | Neurealm | Platinum | Re: Core stock FinOps Dashboard cost differ | P2 | On Hold | 27d | 15-30d | L1 |  | Parthasarathy K |  | 15 Jun 2026 | May 21
#211895 | Neurealm | Platinum | Re: Core stock FinOps Dashboard cost differ for GCP | P3 | On Hold | 27d | 15-30d | L1 |  | Parthasarathy K |  | 15 Jun 2026 | May 21
#211954 | Otsuka | Gold | AWS Accounts transfer from INH to ISO Tenant | P3 | On Hold | 27d | 15-30d | L1 |  | Rajkumar U |  | 22 May 2026 | May 21
#216586 | CoreStack | Bronze | Unable to onboard Snowflake in CS4CS | P3 | Awaiting Resolution Confirmation | 16d | 15-30d | L1 |  | A Bagchi |  | 05 Jun 2026 | Jun 01
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Reason | Last Updated | Created
#217606 | Otsuka | Gold | Login Issue with CoreStack Tool | P3 | Open | 13d | 8-14d | L1 |  | Rajkumar U |  | 17 Jun 2026 | Jun 04
#219258 | CoreStack SRE | Bronze | Firing: [High Priority] MSProd App Server Memory Utilisation above 90% | P3 | Open | 9d | 8-14d | L1 |  | SRE Monitor |  | 08 Jun 2026 | Jun 08
#219593 | Microland | Bronze | Issue with Budget Report Month Selection and Financial Year Setup | P3 | In Progress | 8d | 8-14d | L1 |  | Senapathi R |  | 16 Jun 2026 | Jun 09
#219541 | Sonata Software | Bronze | Trustech - FinOps not triggered | P2 | In Progress | 8d | 8-14d | L1 |  | Krishnakumar VJ |  | 09 Jun 2026 | Jun 09
#217515 | Kyndryl | Gold | FW: Cost Mismatch in recommendation (Kyndryl) | P3 | In Progress | 13d | 8-14d | L1 |  | Nagalakshmi N |  | 04 Jun 2026 | Jun 04
#219147 | Sonata Software | Bronze | RE: CUR Backfill | P3 | On Hold | 9d | 8-14d | L1 |  | Raghavan P |  | 13 Jun 2026 | Jun 08
#217990 | CoreStack | Bronze | cloud.corestack.io is slow across all pages | P3 | On Hold | 12d | 8-14d | L1 |  | Satya C |  | 12 Jun 2026 | Jun 05
#217785 | Cloud Kinetics | Silver | RDS Snapshot Not Created on May 31 | P3 | On Hold | 12d | 8-14d | L1 |  | Cloud Kinetics SA |  | 11 Jun 2026 | Jun 05
#217961 | Sonata Software | Bronze | Sonata - CSP accounts not showing up | P3 | On Hold | 12d | 8-14d | L1 |  | Deovrat S |  | 09 Jun 2026 | Jun 05
#219360 | CoreStack | Bronze | cloud.corestack.io | P3 | On Hold | 9d | 8-14d | L1 |  | Satya C |  | 08 Jun 2026 | Jun 08
#219658 | CoreStack | Bronze | US Prod - Dashboard Not Loading | P3 | Awaiting Resolution Confirmation | 8d | 8-14d | L1 |  | Ashokkumar E |  | 09 Jun 2026 | Jun 09
#219377 | Blackstone | Bronze | ODP Corporation MCA Billing Account cost processing errors | P3 | Awaiting Resolution Confirmation | 9d | 8-14d | L1 |  | Jayven C |  | 08 Jun 2026 | Jun 08
#219361 | Getronics | Silver | Filtrona ¦ FinOps Dashboard ¦ Unallocated Resource Groups | P3 | Awaiting Resolution Confirmation | 9d | 8-14d | L1 |  | Shashank N |  | 08 Jun 2026 | Jun 08
Ticket # | Customer | Band | Subject | Priority | Status | Age | Bucket | Team | ADO # | Raised By | Reason | Last Updated | Created
#219898 | Cloud Kinetics | Silver | Deployment Status Confirmation Required | P3 | Open | 7d | 0-7d | L1 |  | Cloud Kinetics SA |  | 17 Jun 2026 | Jun 10
#220999 | Core42 | Bronze | Request for Investigation – OCI Cost Processing and Cost Optimizer Issues | P3 | Open | 5d | 0-7d | L1 |  | Muthu D |  | 17 Jun 2026 | Jun 12
#222219 | Otsuka | Gold | Request for Azure DevOps Cost Details at Resource Level | P3 | Open | 2d | 0-7d | L1 |  | Rajkumar U |  | 16 Jun 2026 | Jun 15
#222287 | Otsuka | Gold | Confirmation Request – AI (LLM) Cost Details | P3 | Open | 2d | 0-7d | L1 |  | Rajkumar U |  | 16 Jun 2026 | Jun 15
#223020 | CoreStack SRE | Bronze | Firing: [Critical] MSProd-graphdb-01 server load average above 2 | P3 | Open | 0d | 0-7d | L1 |  | SRE Monitor |  | 17 Jun 2026 | Jun 17
#223026 | CoreStack SRE | Bronze | Resolved: [Critical] MSProd-graphdb-01 server load average above 2 | P3 | Open | 0d | 0-7d | L1 |  | SRE Monitor |  | 17 Jun 2026 | Jun 17
#222922 | GE Vernova | Bronze | Memory Spike in GEV Dedicated Prod Environment | P3 | In Progress | 0d | 0-7d | L1 |  | Vijaykumar P |  | 17 Jun 2026 | Jun 17
#222173 | Exide | Bronze | PoV Exide: Unable to execute CIS compliance standard | P3 | In Progress | 2d | 0-7d | L1 |  | Nagalakshmi N |  | 17 Jun 2026 | Jun 15
#222571 | Sonata Software | Bronze | Re: CoreStack - FinOps. Call | P2 | In Progress | 1d | 0-7d | L1 |  | Deovrat S |  | 17 Jun 2026 | Jun 16
#222547 | Otsuka | Gold | Request for Review of Optimization Recommendations (SKU Marked as NA) | P3 | In Progress | 1d | 0-7d | L1 |  | Rajkumar U |  | 16 Jun 2026 | Jun 16
#222218 | Aliando | Bronze | Enable FinOps Governance Summary Report ¦ QapiPlus | P3 | In Progress | 2d | 0-7d | L1 |  | Ajit T |  | 16 Jun 2026 | Jun 15
#222619 | CoreStack | Bronze | FinOps Governance Summary Report ¦ Month field not able to select | P3 | In Progress | 1d | 0-7d | L1 |  | Jayven C |  | 16 Jun 2026 | Jun 16
#222463 | Sonata Software | Bronze | Mismatch in Cost Figures Between Azure Cost Management and CoreStack FinOps | P3 | In Progress | 1d | 0-7d | L1 |  | Thadi S |  | 16 Jun 2026 | Jun 16
#222461 | Kyndryl | Gold | Kyndryl SaaS Okta SSO Configuration | P3 | In Progress | 1d | 0-7d | L1 |  | Nagalakshmi N |  | 16 Jun 2026 | Jun 16
#222257 | Sonata Software | Bronze | Arcera - Replace PAYG to CSP Onboarding | P3 | In Progress | 2d | 0-7d | L1 |  | Krishnakumar VJ |  | 15 Jun 2026 | Jun 15
#222040 | LTTS | Bronze | Billing Amount Difference between GCP and CoreStack | P3 | In Progress | 2d | 0-7d | L1 |  | Kaustubh M |  | 15 Jun 2026 | Jun 15
#222003 | SHI Locuz | Bronze | SHI Locuz - Need Assistance in Compliance Execution & Scheduling | P3 | In Progress | 2d | 0-7d | L1 |  | Nagalakshmi N |  | 15 Jun 2026 | Jun 15
#220546 | Blackstone | Bronze | ODP/Blackstone - Bus Patrol | P3 | In Progress | 6d | 0-7d | L1 |  | Jayven C |  | 11 Jun 2026 | Jun 11
#220105 | CoreStack | Bronze | Merged cells in cost recommendation Report | P3 | In Progress | 7d | 0-7d | L1 |  | Nagalakshmi N |  | 10 Jun 2026 | Jun 10
#220491 | LifeLabs | Bronze | FW: Resources Cost - Beside Tagged and untagged - LifeLabs | P3 | On Hold | 6d | 0-7d | L1 |  | Nagalakshmi N |  | 15 Jun 2026 | Jun 11
#222615 | Logicalis | Gold | Unable to login in Logicalis Cloud Management Portal (CMP) | P3 | Awaiting Resolution Confirmation | 1d | 0-7d | L1 |  | Julio A |  | 17 Jun 2026 | Jun 16
#222631 | CoreStack | Bronze | Taylor Farms - Graphion SBOM workflow - Infra scans getting skipped | P3 | Awaiting Resolution Confirmation | 1d | 0-7d | L1 |  | A Bagchi |  | 16 Jun 2026 | Jun 16
#220875 | Synopsys | Gold | Dashboard slowness | P2 | Awaiting Resolution Confirmation | 5d | 0-7d | L1 |  | Ranjitha T |  | 15 Jun 2026 | Jun 12
#221054 | Kyndryl | Gold | US SaaS - Kyndryl - Default dashboards not visible for tenant/finops_admin | P3 | Awaiting Resolution Confirmation | 5d | 0-7d | L1 |  | Nagalakshmi N |  | 12 Jun 2026 | Jun 12
#220416 | Sonata Software | Bronze | Sonata - Tata Tele CSP processing issue | P2 | Awaiting Resolution Confirmation | 6d | 0-7d | L1 |  | Deovrat S |  | 12 Jun 2026 | Jun 11
#220165 | Sonata Software | Bronze | Trustedtech - HMH - cost for April | P3 | Awaiting Resolution Confirmation | 7d | 0-7d | L1 |  | Krishnakumar VJ |  | 10 Jun 2026 | Jun 10
#219989 | Sonata Software | Bronze | Re: Corestack | P3 | Awaiting Resolution Confirmation | 7d | 0-7d | L1 |  | Deovrat S |  | 10 Jun 2026 | Jun 10